## Sheet1
分项 | 目录 | 完成时间 | 负责人 | 备注
UI资源（非图标） |  | 已经完成 | 杨煜 | 还有四个待确认
UI prefab |  | 2017-12-27 | 杨煜
功能图标和物品图标 | cdn/assetbundles/texture/achievement cdn/assetbundles/texture/campaign cdn/assetbundles/texture/chapter_icon cdn/assetbundles/texture/ingame cdn/assetbundles/texture/portrait cdn/assetbundles/texture/ui_misc cdn/assetbundles/texture/card_icon | 2017-12-29 | 杨煜
| cdn/assetbundles/texture/background cdn/assetbundles/texture/item_icon cdn/assetbundles/texture/garden | 2017-01-04 | 杨煜
声音资源 | streamingassets/audio cdn/assetbundles/audio/sound_effect | 2017-01-08 | 杨煜
动作资源 | cdn/assetbundles/art/role/actions/ingame_dance_actions_anim cdn/assetbundles/art/role/actions/ingame_nodance_actions_anim cdn/assetbundles/art/role/actions/expression | 2017-01-10 | 杨煜
| cdn/assetbundles/art/role/actions/actions_anim cdn/assetbundles/art/role/actions/actions_anim_expression | 2017-01-15 | 杨煜
场景 | Assets\Scenes\Stage[shequ];Art\3d\animations,StaticResources\art\3d\stage\shequ_shatan_02 StaticResources\art\3d\stage,\StaticResources\art\3d\fitment \StaticResources\art\3d\stage\waitingroom_01 StaticResources\art\3d\stage,3d\stage\textures,resources\Art\Note | 2017-01-17 | 杨煜
3D NPC资源 |  | 2017-01-19 | 杨煜
3D相机动画 |  | 2017-01-22 | 杨煜
服饰和服饰图标 | 需要工具支持，移动图标。 | 2017-01-10 | 许亮 | 不是删除，是移到库存
关卡音乐 | /SourceFiles/crossplatform/audio/bgm/ /SourceFiles/crossplatform/level | 2017-12-28 | 许亮 | 不是删除，是移到库存